## Assumptions
Project Cost Estimate - Elder Care Robot Product
Assumption | Value
Project duration (months) | 12
Estimated working hours per month | 176
Employee hourly rate (Toman) | 500000
Trainee hourly rate (Toman) | 250000
Hardware contractor hourly rate (Toman) | 500000
Contingency percentage | 20%
Cost unit | Toman

## Cost Baseline
WBS Items | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | Subtotal
0. Project Management | [12 empty] | 1320000000
Project Manager | 88000000 | 88000000 | 88000000 | 88000000 | 88000000 | 88000000 | 88000000 | 88000000 | 88000000 | 88000000 | 88000000 | 88000000 | 1056000000
Trainee Team Member |  |  |  | 44000000 | 44000000 | 44000000 | 44000000 | 44000000 | 44000000 |  |  |  | 264000000
1. AI Development | [12 empty] | 3432000000
AI Developers | 264000000 | 264000000 | 264000000 | 264000000 | 264000000 | 264000000 | 264000000 | 264000000 | 264000000 | 264000000 | 264000000 | 264000000 | 3168000000
Trainee Team Member |  |  |  | 44000000 | 44000000 | 44000000 | 44000000 | 44000000 | 44000000 |  |  |  | 264000000
2. Hardware Development | [12 empty] | 6056000000
Outside Contractors | 88000000 | 88000000 | 88000000 | 88000000 | 88000000 | 88000000 | 88000000 | 88000000 | 88000000 | 88000000 | 88000000 | 88000000 | 1056000000
Prototype Robots | 5000000000 | [11 empty] | 5000000000
3. Software Development | [12 empty] | 3432000000
Software Developers | 264000000 | 264000000 | 264000000 | 264000000 | 264000000 | 264000000 | 264000000 | 264000000 | 264000000 | 264000000 | 264000000 | 264000000 | 3168000000
Trainee Team Member |  |  |  | 44000000 | 44000000 | 44000000 | 44000000 | 44000000 | 44000000 |  |  |  | 264000000
4. Software-Hardware Integration | [12 empty] | 3584000000
Integration | [6 empty] | 1292000000 | 1292000000 |  |  |  |  | 2584000000
Servers | 1000000000 | [11 empty] | 1000000000
5. Software / Hardware / AI Test | [8 empty] | 1292000000 |  |  |  | 1292000000
6. Marketing Before Launch | [12 empty] | 2028000000
Marketing Employees | [9 empty] | 176000000 | 176000000 | 176000000 | 528000000
Advertising Campaign | [9 empty] | 500000000 | 500000000 | 500000000 | 1500000000
7. Contigency Reserves |  |  | 211440000 | 211440000 | 211440000 | 211440000 | 845760000 | 845760000 | 422880000 | 422880000 | 422880000 | 422880000 | 4228800000
Total | 6704000000 | 704000000 | 915440000 | 1047440000 | 1047440000 | 1047440000 | 2973760000 | 2973760000 | 2550880000 | 1802880000 | 1802880000 | 1802880000 | 25372800000