## Assumptions
Project Cost Estimate - Elder Care Robot Product
Assumption | Value
Project duration (months) | 12
Estimated working hours per month | 176
Employee hourly rate (Toman) | 500000
Trainee hourly rate (Toman) | 250000
Hardware contractor hourly rate (Toman) | 500000
Contingency percentage | 20%
Cost unit | Toman

## Cost Estimate
WBS Items | Qty | Months | Allocation | Units and Hrs. | Cost / (Unit and Hrs.) | Subtotal | WBS Level 2 Subtotals | % of Total Cost | Notes
0. Project Management | [6 empty] | 1320000000 | 5.202%
Project Manager | 1 | 12 | 100% | 2112 | 500000 | 1056000000
Trainee Team Member | 1 | 6 | 100% | 1056 | 250000 | 264000000
1. AI Development | [6 empty] | 3432000000 | 13.53%
AI Developers | 3 | 12 | 100% | 6336 | 500000 | 3168000000
Trainee Team Member | 1 | 6 | 100% | 1056 | 250000 | 264000000
2. Hardware Development | [6 empty] | 6056000000 | 23.87%
Outside Contractors | 2 | 12 | 50% | 2112 | 500000 | 1056000000
Prototype Robots | 100 |  |  |  | 50000000 | 5000000000 |  |  | Prototype robot parts, sensors, boards, actuators and casing
3. Software Development | [6 empty] | 3432000000 | 13.53%
Software Developers | 3 | 12 | 100% | 6336 | 500000 | 3168000000
Trainee Team Member | 1 | 6 | 100% | 1056 | 250000 | 264000000
4. Software-Hardware Integration | [6 empty] | 3584000000 | 14.13%
Integration | [5 empty] | 2584000000 |  |  | 20% of total software / hardware / Ai development cost
Servers | 2 |  |  |  | 500000000 | 1000000000
5. Software / Hardware / AI Test | [5 empty] | 1292000000 | 1292000000 | 5.092% | 10% of total software / hardware / Ai development cost
6. Marketing Before Launch | [6 empty] | 2028000000 | 7.993%
Marketing Employees | 2 | 3 | 100% | 1056 | 500000 | 528000000
Advertising Campaigns | [5 empty] | 1500000000
Subtotal (Cost Definitive Estimate) | [5 empty] | 21144000000
7. Contigency Reserves | [6 empty] | 4228800000 | 16.67%
Total Project Cost Estimate | [6 empty] | 25372800000 | 100%